**ROADMAP FOR THE NEXT PIF FORMULATION/PREPARATION**

The roadmap serves to outline key actions and indicative time horizon to undertake NAIF preparation. Actions presented in the Roadmap are basic steps that lead to timely completion of NAIP. The Road Map does not constitute an exhaustive list of NAIF preparation related actions. It can be reviewed based on comments and inputs from RED&FS SWG Ex COM. The Ex-Com may also need to establish NAIF task force composed of the Government and DPs representatives under the leadership of PPD. The role of the taskforce would be to organize, support and oversee the preparation of NAIF.

**NAIF formulation roadmap**

|  |  |  |  |
| --- | --- | --- | --- |
| **S/N** | **Activity** | **Responsible** | **Timeline** |
| 1 | Created awareness at Ex-COM level on customization of the Malabo Declaration | RED&FS Secretariat | January 2015 |
| 2 | Establish NAIF task force | Ex-COM | Aug 2016 |
| 3 | Develop draft ToR | RED&FS Secretariat | Sept 2016 |
| 4 | Discuss and agree on how to go about enriching the draft ToR | NAIF Task Force | Dec 2016 |
| 5 | Incorporate inputs from NAIF Task Force members and finalize the ToR | RED&FS Secretariat | Jan 2017 |
| 6 | Provide guidance on recruitment of  consultants | Ex-COM Chairs and Co- Charis | Jan 2017 |
| 7 | Kick-start NAIF formulation (data collection & carry out analytical works) | Consultants | Feb 2017 |
| 8 | Develop draft NAIF document | Consultants | March 2017 |
| 9 | Share the daft NAIF document to NAIF Task Force members | Consultants | March 2017 |
| 10 | Share the draft NAIF to stakeholders workshop | Consultants | March 2017 |
| 11 | Present the draft NAIF document to Ex-Com | Consultants | March 2017 |
| 12 | Endorse NAIF | Ex-COM | March 2017 |

Source**:** RED&FS Secretariat, MoANR, December 2016